## Documents
📋 HOW TO USE: Edit rows below to update the dashboard. Status options: Approved ¦ In Review ¦ Pending ¦ Overdue ¦ Draft
Document Name | Document Code | Status | Owner Name | Owner Role | Meeting Date | Committee Cycle | Notes
Asset Class Guidelines – Residential | QIC-CDU-COE-DCM-GDL-000003 | In Review | Simon Cartwright | Senior Director, Cost Planning | 18 Mar 2025 | March N-1 | Progress to March N-1
Monthly Cost Plan Tracker | QIC-CDU-COE-DCM-TRK-000001 | Pending | Simon Cartwright | Senior Director, Cost Planning | 18 Mar 2025 | March N-1 | Awaiting live file from owner
Cost Planning – Roles & Responsibilities | QIC-CDU-COE-DCM-PRO-000008 | Pending | Simon Cartwright | Senior Director, Cost Planning | 18 Mar 2025 | March N-1 | Progress to March N-1 for noting
Internal Document Management Procedure | QIC-CDU-COE-DCM-PRO-000001 | In Review | Rey Santos | Document Management | 18 Mar 2025 | March N-1 | Yellow sections to be completed
Oracle Aconex Service Request & Incident Process Map | QIC-CDU-COE-DCM-PMP-000005 | Approved | Rey Santos | Document Management | 18 Feb 2025 | February N-1 | Approved and filed
Asset Class Guidelines – Commercial | QIC-CDU-COE-DCM-GDL-000004 | Draft | Paul Gilchreaste | Senior Director, Transport Commercial | TBC | April N-1 | Draft in progress
CDU Procurement Policy | QIC-CDU-COE-DCM-POL-000002 | Overdue | Marc Harrison | Sports Cost Planning | 18 Feb 2025 | February N-1 | Escalation required

## Stakeholders
📋 HOW TO USE: Add one row per stakeholder. Match the Document Code exactly to the Documents sheet.
Document Code | Stakeholder Name | Role / Title
QIC-CDU-COE-DCM-GDL-000003 | John Pincini | Executive Director, Master Development Cost Planning
QIC-CDU-COE-DCM-GDL-000003 | Joseph Bailey | Senior Director, Residential Cost Planning
QIC-CDU-COE-DCM-GDL-000003 | Paul Miller | Cost Planning, Hospitality
QIC-CDU-COE-DCM-GDL-000003 | Paul Gilchreaste | Senior Director, Transport Commercial
QIC-CDU-COE-DCM-GDL-000003 | Paolo Petrill | DMO, Culture
QIC-CDU-COE-DCM-GDL-000003 | Matthew Crompton | Senior Director, Entertainment Commercial
QIC-CDU-COE-DCM-GDL-000003 | Marc Harrison | Sports Cost Planning
QIC-CDU-COE-DCM-GDL-000003 | Jagadish Mahendran | Offices, DMO
QIC-CDU-COE-DCM-GDL-000003 | Giovanni Marroccoli | Retail, DMO
QIC-CDU-COE-DCM-TRK-000001 | Jackson Lee | Document Control
QIC-CDU-COE-DCM-TRK-000001 | Rey Santos | Cost Planning
QIC-CDU-COE-DCM-PRO-000001 | Jackson Lee | Document Control
QIC-CDU-COE-DCM-PRO-000001 | Rey Santos | Document Management
QIC-CDU-COE-DCM-PMP-000005 | Rey Santos | Document Management
QIC-CDU-COE-DCM-PMP-000005 | Jackson Lee | Document Control

## Actions
📋 HOW TO USE: Add action items per document. Status options: Open ¦ Complete
Document Code | Action Item | Status | Due Date | Assigned To
QIC-CDU-COE-DCM-GDL-000003 | Confirm stakeholder list changes with Simon | Open | 12 Mar 2025 | Jackson Lee
QIC-CDU-COE-DCM-GDL-000003 | Finalise document for March submission | Open | 14 Mar 2025 | Simon Cartwright
QIC-CDU-COE-DCM-GDL-000003 | Initial draft review completed | Complete | 28 Feb 2025 | Jackson Lee
QIC-CDU-COE-DCM-TRK-000001 | Send live file version (non-PDF) | Open | 10 Mar 2025 | Simon Cartwright
QIC-CDU-COE-DCM-PRO-000001 | Review all highlighted yellow sections | Open | 12 Mar 2025 | Rey Santos
QIC-CDU-COE-DCM-PRO-000001 | Complete metadata gaps – Appendix B SME Working Group | Open | 12 Mar 2025 | Rey Santos
QIC-CDU-COE-DCM-PRO-000001 | Change request form submitted | Complete | 5 Mar 2025 | Rey Santos
QIC-CDU-COE-DCM-PMP-000005 | Process map updated per call | Complete | 4 Mar 2025 | Rey Santos
QIC-CDU-COE-DCM-POL-000002 | Escalation to document owner required | Open | 7 Mar 2025 | Jackson Lee